|  |  |
| --- | --- |
| U.S. Radiocommunications Sector  Fact Sheet | |
| **Working Party:** ITU-R WP 4C | **Document No:** US4C-10 |
| **Ref:** Resolution 249 (WRC-23) | **Date:** 23 February 2024 |
| Document Title: Work Plan for WRC-27 Agenda Item 1.11 | |
| **Author(s)/Contributors(s):**  Brennan Price  Viasat  Tatiana Lawrence  Iridium  Damon Ladson  HWG LLP for Iridium  Wayne Whyte  Teltrium for NASA | Email: [brennan.price@inmarsat.com](mailto:brennan.price@inmarsat.com) [sic] Phone: +1 703 223-3327  Email: [tatiana.lawrence@iridium.com](mailto:tatiana.lawrence@iridium.com)  Phone: +1 240 271-2751  Email: [dladson@hwglaw.com](mailto:dladson@hwglaw.com)  Phone: +1 202 730-1315  Email: [wwhyte@teltrium.com](mailto:wwhyte@teltrium.com)  Phone: +1 202 448-5040 x809 |
| **Purpose:** To propose a schedule of work for studies and CPM text development for WRC-27 agenda item 1.11. | |
| **Abstract:** The contribution will propose objectives for each meeting of Working Party 4C and deadlines for work related to space-to-space links in the mobile-satellite service. | |

|  |  |
| --- | --- |
| **Radiocommunication Study Groups** | A blue logo with a black background  Description automatically generated |
|  |  |
|  |  |
| Received: 23 February 2024  Subject: WRC-27 Agenda Item 1.11; Resolution 249 | **Document US4C/24/10-E** |
| **23 February 2024** |
| **Original: English** |
| **United States of America** | |
| work plan for wrc-27 agenda item 1.11 | |
|  | |

The United States proposes following work plan for WRC-27 agenda item 1.11.

|  |  |
| --- | --- |
| **Milestones** | **Meeting No. 31 (Geneva, 2430 April 2024)**  1 Develop liaison statements to ITU-R contributing groups to request propagation models and characteristics of the existing primary services for the sharing and compatibility studies;  2 Develop a detailed work plan for WRC-27 agenda item 1.11;  3 Develop first version of working documents on sharing and compatibility studies, based on input contributions;  4 Call for contributions in the WP 4C Chair’s Report.  **Meeting No. 32 (Geneva, 16-22 October 2024)**  1 Continue development of working documents on sharing and compatibility studies, based on input contributions;  2 Send liaison statements to contributing groups as necessary;  3 Review and revise the detailed work plan as necessary.  **Meeting No. 33 ([TBD], 1H 2025)**  1 Update working documents on sharing and compatibility studies, based on input contributions;  2 Initiate development of draft CPM text based on input contributions;  3 Send liaison statements to contributing groups as necessary;  4 Review and revise the detailed work plan as necessary.  **Meeting No. 34 ([TBD], 2H 2025)**  1 Update working documents on sharing and compatibility studies, based on input contributions;  2 Update the draft CPM text based on input contributions;  3 Send liaison statements to contributing groups as necessary;  4 Review and revise the detailed work plan as necessary.  **Meeting No. 35 ([TBD], 1H 2026)**  1 Tentatively finalize working documents on sharing and compatibility studies, based on input contributions;\*  2 Finalize the draft CPM text;\*\*  3 Send liaison statements to contributing groups as necessary.  4 Review and revise the detailed work plan as necessary.  **Meeting No. 36 ([TBD], 2H 2026)**  1 Finalize working documents on sharing and compatibility studies, based on input contributions;\*  2 Send liaison statements to contributing groups as necessary.  **Meeting No. 37 ([TBD], [TBD] 2027)**  1 Additional work as necessary based on input contributions;  2 Send liaison statements to contributing groups as necessary.  *\*Note: Finalization of studies will be based on the timing of WRC-27, once established.*  *\*\*Note: Final CPM Text date to be amended once CPM deadline is set.* |