| U.S. Radiocommunications Sector Fact Sheet |  |
| --- | --- |
| Working Party: ITU-R WP 4C | Document No: US4C-10 |
| Ref: Resolution 249 (WRC-23) | Date: 23 February 2024 |
| ## Document Title: Work Plan for WRC-27 Agenda Item 1.11 |  |
| Author(s)/Contributors(s): Brennan Price Viasat Tatiana Lawrence Iridium Damon Ladson HWG LLP for Iridium Wayne Whyte Teltrium for NASA | Email: brennan.price@inmarsat.com [sic] Phone: +1 703 223-3327 Email: tatiana.lawrence@iridium.com Phone: +1 240 271-2751 Email: dladson@hwglaw.com Phone: +1 202 730-1315 Email: wwhyte@teltrium.com Phone: +1 202 448-5040 x809 |
| Purpose: To propose a schedule of work for studies and CPM text development for WRC-27 agenda item 1.11. |  |
| Abstract: The contribution will propose objectives for each meeting of Working Party 4C and deadlines for work related to space-to-space links in the mobile-satellite service. |  |

| Radiocommunication Study Groups |  |
| --- | --- |
| Received: 23 February 2024 Subject: WRC-27 Agenda Item 1.11; Resolution 249 | Document US4C/24/10-E |
|  | 23 February 2024 |
|  | Original: English |
| United States of America |  |
| work plan for wrc-27 agenda item 1.11 |  |

The United States proposes following work plan for WRC-27 agenda item 1.11.

| Milestones | Meeting No. 31 (Geneva, 2430 April 2024) 1 Develop liaison statements to ITU-R contributing groups to request propagation models and characteristics of the existing primary services for the sharing and compatibility studies; 2 Develop a detailed work plan for WRC-27 agenda item 1.11; 3 Develop first version of working documents on sharing and compatibility studies, based on input contributions; 4 Call for contributions in the WP 4C Chair’s Report. Meeting No. 32 (Geneva, 16-22 October 2024) 1 Continue development of working documents on sharing and compatibility studies, based on input contributions; 2 Send liaison statements to contributing groups as necessary; 3 Review and revise the detailed work plan as necessary. Meeting No. 33 ([TBD], 1H 2025) 1 Update working documents on sharing and compatibility studies, based on input contributions; 2 Initiate development of draft CPM text based on input contributions; 3 Send liaison statements to contributing groups as necessary; 4 Review and revise the detailed work plan as necessary. Meeting No. 34 ([TBD], 2H 2025) 1 Update working documents on sharing and compatibility studies, based on input contributions; 2 Update the draft CPM text based on input contributions; 3 Send liaison statements to contributing groups as necessary; 4 Review and revise the detailed work plan as necessary. Meeting No. 35 ([TBD], 1H 2026) 1 Tentatively finalize working documents on sharing and compatibility studies, based on input contributions;* 2 Finalize the draft CPM text;** 3 Send liaison statements to contributing groups as necessary. 4 Review and revise the detailed work plan as necessary. Meeting No. 36 ([TBD], 2H 2026) 1 Finalize working documents on sharing and compatibility studies, based on input contributions;* 2 Send liaison statements to contributing groups as necessary. Meeting No. 37 ([TBD], [TBD] 2027) 1 Additional work as necessary based on input contributions; 2 Send liaison statements to contributing groups as necessary. *Note: Finalization of studies will be based on the timing of WRC-27, once established. **Note: Final CPM Text date to be amended once CPM deadline is set. |
| --- | --- |