|  |
| --- |
| U.S. Radiocommunications SectorFact Sheet |
| **Working Party:** ITU-R WP 4C | **Document No:** US4C-10 |
| **Ref:** Resolution 249 (WRC-23) | **Date:** 22 March 2024 |
| Document Title: Work Plan for WRC-27 Agenda Item 1.11  |
| **Author(s)/Contributors(s):**Brennan PriceViasatTatiana LawrenceIridiumDamon LadsonHWG LLP for IridiumWayne WhyteTeltrium for NASA | Email: brennan.price@inmarsat.com [sic]Phone: +1 703 223-3327Email: tatiana.lawrence@iridium.com Phone: +1 240 271-2751Email: dladson@hwglaw.com Phone: +1 202 730-1315Email: wwhyte@teltrium.com Phone: +1 202 448-5040 x809 |
| **Purpose:** To propose a schedule of work for studies and CPM text development for WRC-27 agenda item 1.11. |
| **Abstract:** The contribution will propose objectives for each meeting of Working Party 4C and deadlines for work related to space-to-space links in the mobile-satellite service. |

|  |  |
| --- | --- |
| **Radiocommunication Study Groups** | A blue logo with a black background  Description automatically generated |
|  |  |
|  |  |
| Received: 22 March 2024Subject: WRC-27 Agenda Item 1.11; Resolution 249 | **Document US4C/24/10-E** |
| **22 March 2024** |
| **Original: English** |
| **United States of America** |
| work plan for wrc-27 agenda item 1.11 |
|  |

The United States proposes following work plan for WRC-27 agenda item 1.11.

|  |  |
| --- | --- |
| **Milestones** | **Meeting No. 31 (Geneva, 2430 April 2024)**1 Develop liaison statements to ITU-R contributing groups to request propagation models and characteristics of the existing primary services for the sharing and compatibility studies;2 Develop a detailed work plan for WRC-27 agenda item 1.11;3 Develop first version of working documents on sharing and compatibility studies, based on input contributions;4 Call for contributions in the WP 4C Chair’s Report.**Meeting No. 32 (Geneva, 16-22 October 2024)**1 Continue development of working documents on sharing and compatibility studies, based on input contributions;2 Send liaison statements to contributing groups as necessary;3 Review and revise the detailed work plan as necessary.**Meeting No. 33 ([TBD], 1H 2025)**1 Update working documents on sharing and compatibility studies, based on input contributions;2 Initiate development of draft CPM text based on input contributions;3 Send liaison statements to contributing groups as necessary;4 Review and revise the detailed work plan as necessary.**Meeting No. 34 ([TBD], 2H 2025)**1 Update working documents on sharing and compatibility studies, based on input contributions;2 Update the draft CPM text based on input contributions;3 Send liaison statements to contributing groups as necessary;4 Review and revise the detailed work plan as necessary.**Meeting No. 35 ([TBD], 1H 2026)**1 Tentatively finalize working documents on sharing and compatibility studies, based on input contributions;\*2 Finalize the draft CPM text;\*\*3 Send liaison statements to contributing groups as necessary.4 Review and revise the detailed work plan as necessary.**Meeting No. 36 ([TBD], 2H 2026)**1 Finalize working documents on sharing and compatibility studies, based on input contributions;\*2 Send liaison statements to contributing groups as necessary.**Meeting No. 37 ([TBD], [TBD] 2027)**1 Additional work as necessary based on input contributions;2 Send liaison statements to contributing groups as necessary.*\*Note: Finalization of studies will be based on the timing of WRC-27, once established.**\*\*Note: Final CPM Text date to be amended once CPM deadline is set.* |