|  |
| --- |
| **U.S. Radiocommunications Sector****Fact Sheet** |
| **Working Party:** ITU-R WP 5B | **Document No:** USWP5B25-FD-25 |
| **Ref:** WRC-23 AI 1.6 | **Date:** September 21, 2020 |
| **Document Title:** Work Plan for WRC-23 AI 1.6 |
| **Author(s)/Contributors(s):**Chris TourignyFAA Spectrum Engineering ServicesMichael TranMITRENader DamavandiSpace Exploration TechnologiesDamon LadsonHarris, Wiltshire & GrannisDonald JanskyGregory BakerAviation Spectrum Resources, Inc. | Phone: 202-267-3071Email: chris.tourigny@faa.govPhone: 703-983-1295 Email: mtran@mitre.orgPhone: 310-219-7854 Email: nader.damavandi@spacex.comPhone: (202) 730-1315 Email: dladson@hwglaw.com Phone: 202-415-1834 Email: don@jansky-barmat.comPhone: (269) 923-9993  Email: gdb@asri.aero |
| **Purpose/Objective:** This document proposes the draft Working Document on the Work Plan of Working Party 5B for WRC-23 agenda item 1.6. |
| **Abstract:** This contribution initiates the draft Working Document on the Work Plan of Working Party 5B for WRC-23 agenda item 1.6 in the Attachment. |

|  |  |
| --- | --- |
| **Radiocommunication Study Groups** |  |
|  |  |
|  |  |
| Source: Subject: WRC-23 agenda item 1.6 | **Document 5B/** |
| **20 November 2020** |
| **English only** |
| United States of America |
| WORKING DOCUMENT ON THE DRAFT WORK PLAN OF WORKING PARTY 5B FOR WRC-23 AGENDA ITEM 1.6 |
|  |

This document proposes the draft Working Document on the Work Plan of Working Party 5B for WRC-23 agenda item 1.6 in the Attachment.

**Attachment:** 1

ATTACHMENT

**Draft Work plan for WRC-23 agenda item 1.6**

|  |
| --- |
| **2020**  |
| 1st WP 5B meeting(July 20-30, 2020) | − Send Liaison Statements (LS) to WP 3M, WP 4A, WP 4С, and WP 7B, requesting information for WRC-23 AI 1.6;− Initiate the draft sharing Report for AI 1.6; |
| 2nd WP 5B meeting(November 9-20, 2020) | − Review reply LS from relevant groups, and collect propagation models and technical information;− Update the draft sharing Report for AI 1.6; |
| **2021** |
| 3rd WP 5B meeting(Spring 2021) | − Continue collection of propagation models and technical information of WP 3M, WP 4C, WP 4A, and WP 7B;− Review reply LS from WP 3M, WP 4C, WP 4A, and WP 7B;− LS to the WP 3M, WP 4C, WP 4A, and WP 7B on the draft sharing Report for AI 1.6;− Continue to develop the draft sharing Report for AI 1.6; |
| 4th WP 5B meeting(Fall 2021) | − Continue to develop the draft sharing Report for AI 1.6;− LS to concerned and interested WPs if necessary;− Initiate the draft CPM Report for AI 1.6 to WRC-23. |
| **2022** |
| 5th WP 5B meeting(Spring 2022) | − Continue to develop the draft sharing Report for AI 1.6;− LS to concerned and interested WPs if necessary;− Update the draft CPM Report for AI 1.6 to WRC-23. |
| 6th WP 5B meeting(Fall 2022) | − Finalize the sharing Report for AI 1.6;− Finalize the draft CPM Report for AI 1.6 to WRC-23.  |