| U.S. Radiocommunications Sector Fact Sheet |  |  |
| --- | --- | --- |
| Working Party: ITU-R WP 5B | Document No: USWP5B25-25 |  |
| Ref: WRC-23 AI 1.6 | Date: September 21, 2020 |  |
| Document Title: Work Plan for WRC-23 AI 1.6 |  |  |
| Author(s)/Contributors(s): Chris Tourigny FAA Spectrum Engineering Services Michael Tran MITRE Nader Damavandi Space Exploration Technologies Damon Ladson Harris, Wiltshire & Grannis Donald Jansky Gregory Baker Aviation Spectrum Resources, Inc. |  | Phone: 202-267-3071 Email: chris.tourigny@faa.gov Phone: 703-983-1295 Email: mtran@mitre.org Phone: 310-219-7854 Email: nader.damavandi@spacex.com Phone: (202) 730-1315 Email: dladson@hwglaw.com Phone: 202-415-1834 Email: don@jansky-barmat.com Phone: (269) 923-9993 Email: gdb@asri.aero |
| Purpose/Objective: This document proposes the draft Working Document on the Work Plan of Working Party 5B for WRC-23 agenda item 1.6. |  |  |
| Abstract: This contribution initiates the draft Working Document on the Work Plan of Working Party 5B for WRC-23 agenda item 1.6 in the Attachment. |  |  |

| Radiocommunication Study Groups |  |
| --- | --- |
| Source: Subject: WRC-23 agenda item 1.6 | Document 5B/ |
|  | 20 November 2020 |
|  | English only |
| United States of America |  |
| WORKING DOCUMENT ON THE DRAFT WORK PLAN OF WORKING PARTY 5B FOR WRC-23 AGENDA ITEM 1.6 |  |

This document proposes the draft Working Document on the Work Plan of Working Party 5B for WRC-23 agenda item 1.6 in the Attachment.

Attachment:	1

ATTACHMENT

Draft Work plan for WRC-23 agenda item 1.6

| 2020 |  |
| --- | --- |
| 1st WP 5B meeting (July 20-30, 2020) | − Send Liaison Statements (LS) to WP 3M, WP 4A, WP 4С, and WP 7B, requesting information for WRC-23 AI 1.6; − Initiate the draft sharing Report for AI 1.6; |
| 2nd WP 5B meeting (November 9-20, 2020) | − Review reply LS from relevant groups, and collect propagation models and technical information; − Update the draft sharing Report for AI 1.6; |
| 2021 |  |
| 3rd WP 5B meeting (Spring 2021) | − Continue collection of propagation models and technical information of WP 3M, WP 4C, WP 4A, and WP 7B; − Review reply LS from WP 3M, WP 4C, WP 4A, and WP 7B; − LS to the WP 3M, WP 4C, WP 4A, and WP 7B on the draft sharing Report for AI 1.6; − Continue to develop the draft sharing Report for AI 1.6; |
| 4th WP 5B meeting (Fall 2021) | − Continue to develop the draft sharing Report for AI 1.6; − LS to concerned and interested WPs if necessary; − Initiate the draft CPM Report for AI 1.6 to WRC-23. |
| 2022 |  |
| 5th WP 5B meeting (Spring 2022) | − Continue to develop the draft sharing Report for AI 1.6; − LS to concerned and interested WPs if necessary; − Update the draft CPM Report for AI 1.6 to WRC-23. |
| 6th WP 5B meeting (Fall 2022) | − Finalize the sharing Report for AI 1.6; − Finalize the draft CPM Report for AI 1.6 to WRC-23. |