|  |  |  |
| --- | --- | --- |
| **U.S. Radiocommunications Sector**  **Fact Sheet** | | |
| **Working Party:** ITU-R WP 5B | **Document No:** USWP5B25-25 | |
| **Ref:** WRC-23 AI 1.6 | **Date:** September 21, 2020 | |
| **Document Title:** Work Plan for WRC-23 AI 1.6 | | |
| **Author(s)/Contributors(s):**  Chris Tourigny  FAA Spectrum Engineering Services  Michael Tran  MITRE  Nader Damavandi  Space Exploration Technologies  Damon Ladson  Harris, Wiltshire & Grannis  Donald Jansky  Gregory Baker  Aviation Spectrum Resources, Inc. | | Phone: 202-267-3071  Email: chris.tourigny@faa.gov  Phone: 703-983-1295  Email: mtran@mitre.org  Phone: 310-219-7854  Email: nader.damavandi@spacex.com  Phone: (202) 730-1315  Email: [dladson@hwglaw.com](mailto:dladson@hwglaw.com)  Phone: 202-415-1834  Email: don@jansky-barmat.com  Phone: (269) 923-9993  Email: gdb@asri.aero |
| **Purpose/Objective:** This document proposes the draft Working Document on the Work Plan of Working Party 5B for WRC-23 agenda item 1.6. | | |
| **Abstract:** This contribution initiates the draft Working Document on the Work Plan of Working Party 5B for WRC-23 agenda item 1.6 in the Attachment. | | |

|  |  |
| --- | --- |
| **Radiocommunication Study Groups** |  |
|  |  |
|  |  |
| Source:  Subject: WRC-23 agenda item 1.6 | **Document 5B/** |
| **20 November 2020** |
| **English only** |
| United States of America | |
| WORKING DOCUMENT ON THE DRAFT WORK PLAN OF WORKING PARTY 5B FOR WRC-23 AGENDA ITEM 1.6 | |
|  | |

This document proposes the draft Working Document on the Work Plan of Working Party 5B for WRC-23 agenda item 1.6 in the Attachment.

**Attachment:** 1

ATTACHMENT

**Draft Work plan for WRC-23 agenda item 1.6**

|  |  |
| --- | --- |
| **2020** | |
| 1st WP 5B meeting  (July 20-30, 2020) | − Send Liaison Statements (LS) to WP 3M, WP 4A, WP 4С, and WP 7B, requesting information for WRC-23 AI 1.6;  − Initiate the draft sharing Report for AI 1.6; |
| 2nd WP 5B meeting  (November 9-20, 2020) | − Review reply LS from relevant groups, and collect propagation models and technical information;  − Update the draft sharing Report for AI 1.6; |
| **2021** | |
| 3rd WP 5B meeting  (Spring 2021) | − Continue collection of propagation models and technical information of WP 3M, WP 4C, WP 4A, and WP 7B;  − Review reply LS from WP 3M, WP 4C, WP 4A, and WP 7B;  − LS to the WP 3M, WP 4C, WP 4A, and WP 7B on the draft sharing Report for AI 1.6;  − Continue to develop the draft sharing Report for AI 1.6; |
| 4th WP 5B meeting  (Fall 2021) | − Continue to develop the draft sharing Report for AI 1.6;  − LS to concerned and interested WPs if necessary;  − Initiate the draft CPM Report for AI 1.6 to WRC-23. |
| **2022** | |
| 5th WP 5B meeting  (Spring 2022) | − Continue to develop the draft sharing Report for AI 1.6;  − LS to concerned and interested WPs if necessary;  − Update the draft CPM Report for AI 1.6 to WRC-23. |
| 6th WP 5B meeting  (Fall 2022) | − Finalize the sharing Report for AI 1.6;  − Finalize the draft CPM Report for AI 1.6 to WRC-23. |