Revised USWP1A/SG1 Preparatory Schedule

| Start |  | End Date | Item |
| --- | --- | --- | --- |
| Date | Time |  |  |
| 2 Feb 26 |  |  | Call for Fact Sheets for possible US Contributions to WP1A distributed |
| 11 Feb 26 |  |  | Fact Sheets are due by 12pm |
| 23 Feb 26 | 3:00pm |  | 1st meeting of WP1A/SG1 US prep process |
| 9 March 26 |  |  | First drafts are due by 12pm |
| 16 March 26 | 2:00pm |  | 2nd meeting of WP1A/SG US prep process |
| 6 April 26 |  |  | Updated drafts are due by 12pm |
| 13 April 26 | 1:00pm |  | 3rd meeting of WP1A/SG1 US prep process |
| 22 April 26 |  |  | Final drafts are due by 12pm |
| 27 April 26 | 2:00pm |  | 4th and final meeting of WP1A/SG1 US prep process |
| 28 April 26 |  |  | National Committee versions of draft due by 12pm |
| 29 April 26 |  | 5 May 26 | National Committee Review Interval to review differences |
| 6 May 26 |  | 21 May 26 | Interval for Reconciliation (NTIA/FCC/State) and clearance as needed |
| 22 May 26 |  |  | ITU Contribution Deadline (due by 11am) |
| 26 May 26 | 1:00 pm |  | USWP1A/SG1 delegation meeting |
| 3 June 26 |  | 10 June 26 | Working Parting 1A Meeting (Geneva, Planned) |
| 11 June 26 |  | 11 June 26 | Study Group 1 meeting |
| 11 June 26 |  | 11 June 26 | Study Group 1 meeting |

*All times are Eastern