Proposed preparatory schedule (sent in email 11 August 2020)

• 11 August 2020 (Tuesday) = Call for Fact Sheets for possible US contributions to WP1A distributed

• 21 August 2020 (Friday) = Fact Sheets due

• 25 August 2020 (Tuesday) = 1st meeting of WP1A/SG1 US prep process (9:30 am eastern)

• 18 September 2020 (Friday) = First drafts due

• 22 September 2020 (Tuesday) = 2nd meeting of WP1A/SG1 US prep process (9:30 am eastern)

• 14 October 2020 (Wednesday) = Final drafts due

• 19 October (Monday)= 3rd and final meeting of WP1A/SG1 US prep process (9:30 am eastern)

• 19 October (Monday) = Final National Committee review versions due by 5 pm Eastern

• 20 October (Tuesday) = Documents enter National Committee review

• 3 November (Tuesday) = Close of National Committee review (with gap before ITU deadline to allow for any reconciliation required)

• 17 November 2020 (Tuesday) = Deadline for contributions to the ITU

• 24 November – 2 December 2020 (Tuesday - Wednesday) = Working Party 1A meeting

• • 3 December 2020 (Thursday) = Study Group 1 meeting